Guide 2. APT Project Development

Capstone Course

1. Summary of APT Project Progress

Below you will find several fields that you must complete with the requested information.

| Summary of APT project progress | During the first seven weeks of the APT project, work progressed from planning to building the system for Ecoterra. Requirements gathering and organization, architecture definition, the data model, the interface prototype, and feature prioritization through a Product Backlog were completed. During development, the interfaces for the system’s three modules (operations and inventory management; quotations and invoicing; artificial intelligence) were built and reviewed. Reviewing and providing feedback on each page made it possible to identify missing elements, visual adjustments, and inconsistencies with the data model. As a result, the database and Data Dictionary were updated to include necessary tables and attributes, particularly for roles and permissions, inventory, movements, quotations, and credit notes. Additionally, at the start of development, developer Ethan Silvestre identified a Figma tool that could transform the prototype into the final frontend. Therefore, during weeks 5 and 6, priority was given to building the system’s complete frontend rather than developing each feature alongside its backend, which led to an adjustment of the initially planned methodology. Current status: In week 7, the frontend was reviewed as a whole and confirmed to be complete and ready for the next phase. At the same time, Benjamín Mateluna began Sprint 2 (backend and integration of Module 1). Thus, the frontend is complete and the backend is under development. The backend will be built and integrated progressively by module through an API that enables communication between the frontend and the system’s services. Django REST Framework provides tools for developing and documenting web APIs, making it easier to expose backend resources and operations (Django REST framework, n.d.). |
| --- | --- |
| Objectives | The initial objectives remain valid, since the adjustment involved reorganizing the development strategy and sequence rather than changing the project’s purpose. Only the KPIs were adjusted to set more realistic targets. General objective: Develop an information system to manage customers, inventory, quotations, and invoicing, incorporating predictive models for Ecoterra. Specific objectives and progress status: - SO1. Analyze and document the system’s functional and non-functional requirements, defining its architecture and data structure according to Ecoterra’s needs. (KPI: 100 % of requirements defined and validated by the client, with the data model and architecture documented.) Status: Completed during the planning and analysis stage. The requirements, architecture, data model, and related documentation are available. 100% of the defined requirements were documented and validated by the client. During development, the data model was updated based on the reviews conducted. - d - SO2. Develop the operations and inventory management module to manage customers, addresses, products, users, stock levels, and inventory movements. (KPI: 90 % of the prioritized Module 1 features implemented and verified through test cases.) Status: In development. The module interfaces have been built and are being integrated with the backend during Sprint 2. - SO3. Develop the quotations and invoicing module to manage quotations, purchase orders, invoices, credit notes, and related PDF documents. (KPI: 90 % of the prioritized Module 2 features implemented and verified through test cases.) Status: Development pending. The corresponding interfaces have already been incorporated into the frontend. Backend development and integration are planned for Sprints 3 and 4. - SO4. Implement and integrate three predictive models using Scikit-Learn to estimate arrival times, prices, and inventory replenishment needs. (KPI: All 3 predictive models implemented, evaluated using performance metrics, and accessible through the system.) Status: Development pending. The corresponding interfaces have already been incorporated into the frontend. Development of the predictive models and their integration with the backend are planned for Sprint 5. Scikit-learn is a machine-learning library that provides tools for developing and evaluating predictive models, and will therefore support implementation of the solutions included in this objective (Pedregosa et al., 2011). |
| Methodology | The project continues to use the Scrum framework, adapted to the academic context and with the previously defined roles. Its plan is organized into the three phases established by the course: - Phase 1 – Planning: weeks 1–4. - Phase 2 – Development: weeks 5–15. - Phase 3 – Presentation and closure: weeks 16–18. Scrum proposes an iterative and incremental approach based on frequent inspection of the work and adaptation of the process to respond to change and improve results (Schwaber & Sutherland, 2020). Following the monitoring carried out during Sprint 1, the development sequence was adjusted. The initial plan was to progress feature by feature; however, because the final frontend could be developed in advance, the Sprints were reorganized to separate frontend construction from backend development and integration. The new organization includes: - Sprint 1 — Weeks 5–6: initial development and completion of the frontend. - Sprint 2 — Weeks 7–8: backend and integration of Module 1. - Sprint 3 — Weeks 9–10: backend and integration of quotations and purchase orders. - Sprint 4 — Weeks 11–12: invoicing, credit notes, PDFs, and email. - Sprint 5 — Weeks 13–14: implementation and integration of the three predictive models. The methodology’s main deliverables and management evidence include: - Product Vision: definition of the product’s vision and purpose. - Product Backlog: record and prioritization of required features. - Tracking board: organization and monitoring of the tasks selected for each Sprint. - Definition of Done: criteria used to determine when a task or feature can be considered complete. - Sprint sheets: documentation of each Sprint’s objectives, tasks, results, and progress. - Retrospectives: record of positive aspects, difficulties, and improvement actions identified at the end of each Sprint. Applying this methodology enables continuous progress monitoring and planning adjustments when development conditions require them. |
| Progress Evidence | The selected evidence demonstrates both the project’s technical progress and the correct application of the Scrum framework. Management and methodology evidence: The following evidence is presented: - Product Vision - Product Backlog - Trello board - Definition of Done - Sprint 1 Sheet - Sprint 1 Retrospective Technical evidence: Evidence of system development is also presented, including: - Frontend interfaces for the three modules. - Reviews and feedback provided on the interfaces. - Updated database model. - Updated Data Dictionary. - Evidence of the start of backend development for Module 1. The evidence presented confirms that the project has progressed from analysis and design to implementation, maintaining alignment among defined requirements, technical design, development, and Scrum monitoring activities. Project quality has been safeguarded through periodic interface reviews, verification that interfaces align with requirements and the Data Dictionary, updates to the data model when inconsistencies were identified, and work monitoring using Scrum planning and management tools. |

Technical evidence:

- Updated database model:

- Link to updated Data Dictionary

- Evidence of the start of the Sprint 2 backend (screenshots of backend-frontend synchronization):

- Frontend screenshots:

2. Work Plan Monitoring

Carefully examine your work plan, focusing especially on the progress status and adjustments column.

| Milestone 1 — Analysis and Design |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competency unit | Activities | Resources | Activity duration | Person responsible | Notes | Progress status | Adjustments |
| C2 | Requirements gathering. | Google Meet, Google Docs, Trello, project documentation | W1–W2 | Araceli Vega | Ongoing communication with the client and validation of their needs were necessary. | Completed | The activity was carried out according to the initial plan. |
| C2 | Requirements validation | Requirements document and meetings with the client | W3 | Araceli Vega | Reviews were conducted to confirm the functional scope. | Completed | The activity was retained, with specific clarifications made during development when necessary. |
| C1 and C4 | Architecture design | UML diagrams, technical documentation, Git/GitHub | W3–W4 | Ethan Silvestre | The architecture was defined with the project’s modules and technologies in mind. | Completed | The activity remained as planned. A technical review is planned during development to ensure proper integration. |
| C1 and C4 | Database and prototype design | PostgreSQL, Figma, Data Dictionary, diagrams | W3–W4 | Kryshsna Cerda / Ethan Silvestre | The initial design served as the basis for development, but some structures required changes when implementation began. | Adjusted | Elements of the data model and Data Dictionary were updated during development, adding roles, permissions, movements associated with inventory/batches, and other attributes required by the features. |

APT Work Plan Monitoring

Based on the monitoring of the initial Work Plan, the four milestones defined for the APT Project were maintained. However, the distribution of the activities associated with each milestone was adjusted to reflect the team's actual progress and organize development into Sprints lasting a maximum of two weeks.

The main modification concerns the development stage. While the initial plan distributed activities according to weeks and modules, the new organization uses Sprints as the units for execution and monitoring. Accordingly, Milestone 2 is carried out through Sprints 1 and 2; Milestone 3 through Sprints 3 and 4; and Milestone 4 through Sprint 5 and the final integration and testing stage.

| Milestone 2 — Operations Management Module |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competency units | Activities | Resources | Activity duration | Person responsible | Notes | Progress status | Adjustments |
| C4 | Frontend completion — Module 1 | React, Tailwind CSS, Figma, Git/GitHub | W5–W6 — Sprint 1 | Ethan Silvestre | Interfaces for the main features of Module 1 were developed. | Completed | Frontend development for these features was concentrated in Sprint 1 rather than being developed simultaneously with the backend. |
| C3 and C4 | Frontend completion — Module 2 | React, Tailwind CSS, Figma, Git/GitHub | W5–W6 — Sprint 1 | Ethan Silvestre | Interfaces for the main features of Module 2 were developed. | Completed | Frontend development for these features was concentrated in Sprint 1 rather than being developed simultaneously with the backend. |
| C3 and C4 | Frontend completion — Module 3 | React, Tailwind CSS, Figma, Git/GitHub | W5–W6 — Sprint 1 | Ethan Silvestre | Interfaces for the main features of Module 3 were developed. | Completed | Frontend development for these features was concentrated in Sprint 1 rather than being developed simultaneously with the backend. |
| C4 | Frontend completion — Overall review of the three modules | Figma, React, Tailwind CSS, requirements, Data Dictionary | W6–W7 — Sprint 1 / transition to Sprint 2 | Ethan Silvestre / Araceli Vega | The developed interfaces were reviewed and adjustments were identified before integration. | Completed | An explicit frontend review stage was added before backend integration began. |
| C4 | Backend development for customers and addresses | Django REST Framework, PostgreSQL, Git/GitHub | W7–W8 — Sprint 2 | Benjamín Mateluna | Backend development begins once the corresponding frontend has been reviewed. | In progress | This was moved from general Module 1 development to a dedicated backend and integration Sprint. |
| C4 | Backend development for products, inventory, and batches | Django REST Framework, PostgreSQL, Git/GitHub | W7–W8 — Sprint 2 | Benjamín Mateluna | Inventory rules and the relationship between products and batches must be validated. | In progress | Batch management was explicitly included, and the data model was updated to support it. |
| C3 and C4 | Backend development for inventory movements | Django REST Framework, PostgreSQL, React, Git/GitHub | W7–W8 — Sprint 2 | Benjamín Mateluna / Ethan Silvestre | Movements must be correctly associated with the relevant inventory/batch. | In progress | The data model was modified by adding id_inventario to MOVIMIENTO and removing id_producto from this table. |
| C3 and C4 | Backend development for users, roles, permissions, and authentication | Django REST Framework, PostgreSQL, React, Git/GitHub | W7–W8 — Sprint 2 | Benjamín Mateluna / Ethan Silvestre | Coordination between frontend and backend is required to implement configurable permissions. | In progress | The direct role field in USUARIO was replaced by a structure based on ROL, PERMISO, and ROL_PERMISO, in addition to adding id_rol to USUARIO. |
| C4 | Backend development for suppliers | Django REST Framework, PostgreSQL, React, Git/GitHub | W7–W8 — Sprint 2 | Benjamín Mateluna | It must be integrated with the previously developed frontend interface. | In progress | It was reorganized within Sprint 2 alongside the other backend features of Module 1. |
| C4 | Module 1 integration and testing | Test cases, developed system, Git/GitHub | W8 — Sprint 2 | Benjamín Mateluna / Kryshsna Cerda | It will be carried out once the priority backend features have been implemented. | Not started | It was moved to the end of Sprint 2 to validate the complete increment, not just the frontend interfaces. |

| Milestone 3 — Quotations and Invoicing |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Unidad de competencias | Activities | Resources | Activity duration | Person responsible | Notes | Progress status | Adjustments |
| C4 | Backend development for quotations and quotation details | React, Django REST Framework, PostgreSQL, Git/GitHub | W9–W10 — Sprint 3 | Benjamín Mateluna | Requires information from customers and products. | Not started | It was reorganized as the first part of Sprint 3, prioritizing the start of the commercial workflow. |
| C4 | Backend development for purchase orders | Django REST Framework, PostgreSQL, React, Git/GitHub | W9–W10 — Sprint 3 | Benjamín Mateluna / Ethan Silvestre | The relationship between the quotation and purchase order must be validated where applicable. | Not started | The workflow was reorganized to implement quotations first and then associate them with purchase orders. |
| C4 | Association between purchase orders and quotations | React, Django REST Framework, PostgreSQL | W9–W10 — Sprint 3 | Benjamín Mateluna / Ethan Silvestre | It must correctly establish the relationship between both documents. | Not started | It was separated as a functional activity within Sprint 3 to facilitate validation of the workflow from quotation to purchase order. |
| C4 | Module 2 integration — commercial stage | Test cases, developed system, Git/GitHub | W10 — Sprint 3 | Benjamín Mateluna / Ethan Silvestre | It will be run once the priority backend features are implemented | Not started | It was reorganized as the final part of Sprint 3, prioritizing value delivery. |
| C4 | Development of invoicing and invoice details | Django REST Framework, PostgreSQL, React, Git/GitHub | W11–W12 — Sprint 4 | Benjamín Mateluna / Ethan Silvestre | It depends on purchase orders functioning correctly. | Not started | It was moved to Sprint 4 to maintain a logical sequence: quotation → purchase order → invoice. |
| C4 | Development of credit notes | Django REST Framework, PostgreSQL, React, Git/GitHub | W11–W12 — Sprint 4 | Benjamín Mateluna | Credit notes must be associated with the corresponding invoice. | Not started | It was explicitly included in Sprint 4, and the data model was updated with numero_nc. |
| C4 | Generation and storage of commercial documents in PDF format | Django, ReportLab, React, PostgreSQL | W11–W12 — Sprint 4 | Ethan Silvestre / Benjamín Mateluna | The documents must be available for consultation. | Not started | It was grouped with invoicing to fully integrate the commercial documents. |
| C4 | Sending quotations and invoices by email | Django, email service, React, Git/GitHub | W11–W12 — Sprint 4 | Ethan Silvestre | It depends on the correct generation of PDF documents. | Not started | It was defined as a specific task within Sprint 4 to facilitate implementation and validation. |
| C4 | Full Module 2 integration | Test cases, developed system, Git/GitHub | W12 — Sprint 4 | Ethan Silvestre / Benjamín Mateluna | It will be carried out once the priority backend features have been implemented. | Not started | It was reorganized as the final activity of Sprint 4, prioritizing value delivery. |

| Milestone 4 — AI and Integration |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competency or competency units | Activities | Resources | Activity duration | Person responsible | Notes | Progress status | Adjustments |
| C1 and C4 | Dataset preparation and cleaning | Python, CSV, PostgreSQL, Git/GitHub | W13 — Sprint 5 | Araceli Vega / Kryshsna Cerda | Initially, some historical data may be simulated. | Not started | It was moved to the beginning of Sprint 5 to prepare the data before training the models. |
| C1 and C4 | Arrival-time prediction model | Python, Scikit-Learn, datasets | W13–W14 — Sprint 5 | Araceli Vega / Kryshsna Cerda | The model’s error and behavior must be evaluated. | Not started | It was included in a shared AI Sprint with the other models to facilitate subsequent integration. |
| C1 and C4 | Price prediction model | Python, Scikit-Learn, datasets, PostgreSQL | W13–W14 — Sprint 5 | Araceli Vega / Kryshsna Cerda | The variables used and their availability must be validated. | Not started | It was reorganized to be developed alongside the other predictive models. |
| C1 and C4 | Stock replenishment prediction model | Python, Scikit-Learn, PostgreSQL, datasets | W13–W14 — Sprint 5 | Araceli Vega / Kryshsna Cerda | It uses information related to inventory and sales. | Not started | It was included in the same AI model development cycle to facilitate joint data preparation and integration. |
| C1 and C4 | Integration of models with the backend | Python, Scikit-Learn, Django REST Framework, APIs, Git/GitHub | W14 — Sprint 5 | Benjamín Mateluna / Kryshsna Cerda | Adjustments may be needed when integrating the models with the backend and frontend. | Not started | Integration was moved to a stage after model development, within the same Sprint 5. |
| C1 and C4 | Integration of the artificial intelligence dashboard | Python, Scikit-Learn, Django REST Framework, APIs, Git/GitHub | W14 — Sprint 5 | Benjamín Mateluna / Kryshsna Cerda | It requires all three models to be working correctly. | Not started | Integration was moved to a stage after model development, within the same Sprint 5. |
| C4 | Overall integration and final testing | Test cases, complete system, Git/GitHub | W15 | Entire team | All three modules and the predictive models must be considered. | Not started | A dedicated week was set aside for integration and final testing, separate from feature development. |
| C3 | Validation, preparation of the final report, documentation, and presentation preparation | Word/Google Docs, PowerPoint, evidencias, Trello | W16–W18 | Entire team | Documentation and presentation tasks will be distributed among team members. | Not started | The original plan is retained, incorporating evidence generated during the new Sprints and documenting the adjustments made. |

| Scrum Activity |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competency or competency units | Activities | Resources | Activity duration | Person responsible | Notes | Progress status | Adjustments |
| C3 | Definition and management of the Product Backlog | Trello, requirements | W1–W18 | Araceli Vega | The backlog may be modified based on validation and duly justified changes. | In progress | It remains an ongoing activity, incorporating new technical tasks resulting from the reorganization. |
| C3 | Sprint Planning | Trello, Product Backlog, Sprint Backlog | Beginning of each Sprint | Kryshsna Cerda / Todo el equipo | It establishes the objective and work for each Sprint. | In progress | Planning shifted from being primarily centered on weeks/milestones to being specific to each Sprint. |
| C3 | Daily Scrum and progress tracking | Trello, progress tracking records, Google Meet | W5–W15 | Entire team | It helps identify progress, pending tasks, and impediments. | In progress | It remains an ongoing activity, and Trello is used to visualize task status. |
| C3 | Sprint Review | System, prototypes, evidence, Google Meet | End of each Sprint | Entire team / Araceli Vega | It allows the increment to be reviewed and necessary adjustments to be determined. | In progress | It was reorganized to take place at the end of each Sprint, rather than using only milestones as review points. |
| C3 | Sprint Retrospective | Sprint records, Trello, meeting minutes | End of each Sprint | Entire team / Kryshsna Cerda | It helps identify improvements for the next cycle. | In progress | It remains a continuous-improvement activity, with agreements considered in the following Sprint. |
| C3 | Record of progress, impediments, and agreements | Trello, records, documents, Git/GitHub | W1–W18 | Entire team / Kryshsna Cerda | It provides a record of the process and decisions made. | In progress | Progress and agreements were documented more thoroughly due to changes in planning and development organization. |

3. Adjustments Based on Monitoring

Go deeper into the observations of your work plan. Analyze the planned activities and point out which aspects facilitated or hindered the execution of the plan. Explain how you addressed and/or will address the obstacles. Finally, indicate the adjustments you made to the work plan based on this analysis.

Factors that have facilitated and/or hindered the progress of my work plan: The main factors that facilitated development include organization through Scrum, the use of Trello to track tasks, and the availability of tools and technologies such as Figma, React, Git/GitHub, and Django. Coordination among team members also made it possible to distribute responsibilities according to each person’s area of work. The main difficulties included the need to adapt some interfaces and data structures during development, particularly for user, role, permission, and inventory management. To address these difficulties, the frontend was reviewed, the data model was updated, and tasks were reorganized by Sprint before integration continued.

Actividades ajustadas o eliminadas: No significant activities within the project scope were removed. The main adjustments concerned the sequence and distribution of planned activities. Frontend development for all three modules was brought forward and concentrated in Sprint 1, while backend development and integration were scheduled for subsequent Sprints. Activities related to user, role, and permission management, inventory movements, and data structure were also adjusted in response to needs identified during development. These changes preserve the defined objectives and features while adapting their implementation to the project’s actual progress.

Activities not yet started or delayed: Module 1 backend activities are in progress, while quotation, invoicing, and predictive-model activities have not yet started due to the new Sprint sequence defined for the project. To avoid negative impacts on development, implementation will continue progressively by Sprint, with integration and testing activities included at the end of each cycle. This approach aims to identify potential difficulties early and maintain progress toward the established milestones and objectives.

4. References

- Django REST framework. (n.d.). Documenting your API. Retrieved from https://www.django-rest-framework.org/topics/documenting-your-api/

- Pedregosa, F., Varoquaux, G., Gramfort, A., Michel, V., Thirion, B., Grisel, O., Blondel, M., Prettenhofer, P., Weiss, R., Dubourg, V., VanderPlas, J., Passos, A., Cournapeau, D., Brucher, M., Perrot, M., & Duchesnay, É. (2011). Scikit-learn: Machine learning in Python. Journal of Machine Learning Research, 12, 2825–2830. Retrieved from https://jmlr.org/papers/v12/pedregosa11a.html

- Schwaber, K., & Sutherland, J. (2020). The Scrum Guide: The Definitive Guide to Scrum: The Rules of the Game. Retrieved from https://scrumguides.org/scrum-guide.html